## SINGLE STOREY BANGLO 3M
WORK PROGRAME ( 3 Three Months )
DURATION, WORKERS AND MOBILE CRANE FOR SINGLE STOREY BANGLO - 1500ft2/unit
BILL | DESCRIPTION | No.of workers /Team | No of Worker Required | MOBILE CRANE
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
1 | SURVEY SETTING UP & LEVEL SIM PLAT INSTALLED (1 BLOCK) | 2+0 | 2
2 | INSTALLATION OF PANEL WALL (2UNIT/DAY) | 4+1 | 5 | CR 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | INSTALL REBAR ( 2 DAY/UNIT) | 6+0 | 18 | CR 2
4 | INSTALL & COLUMN MOULD (2 DAY/UNIT) | 6+0 | 18
5 | CASTING COLUMN (1 UNIT/DAY) | 6+0 | 12 | CR 3 | bar: 6 to 45
6 | INSTALLATION BEAM MOULD & REBAR (2 DAYS/UNIT) | 8+0 | 8 | CR2 | bar: 8 to 45
7 | CONCRETING BEAM | 5+0 | 5 | CR3 | bar: 9; 11; 13; 15; 17; 19; 21; 23; 25; 27; 29; 31; 33; 35; 37; 39; 41; 43; 45
[5 empty] | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92
1 | SURVEY SETTING UP & LEVEL SIM PLAT INSTALLED (1 BLOCK) | 2+0 | 2
2 | INSTALLATION OF PANEL WALL (2 UNIT/DAY) | 4+1 | 5 | CR 1 | 56: Total 84 units
3 | INSTALL REBAR ( 2 DAY/UNIT) | 6+0 | 18 | CR 2 | bar: 46 to 87
4 | INSTALL & COLUMN MOULD (2 DAY/UNIT) | 6+0 | 18
5 | CASTING COLUMN (1 UNIT/DAY) | 6+0 | 12 | CR 3
6 | INSTALLATION BEAM MOULD & REBAR (2 DAYS/UNIT) | 8+0 | 8 | CR2
7 | CONCRETING BEAM | 5+0 | 5 | CR3 | bar: 47; 49; 51; 53; 55; 57; 59; 61; 63; 65; 67; 69; 71; 73; 75; 77; 79; 81; 83; 85; 87; 89; 91
TOTAL |  |  | 68
** | 1 Month allowed 4 to 5 days for weekend

## DOUBLE STOREY TERRACE HOUSE
WORK PROGRAME
DURATION, WORKERS AND MOBILE CRANE FOR DOUBLE STOREY TERRACE HOUSE （TYPE A BLOCK 1 - 10 UNITS) - 2500ft2/unit
BILL | DESCRIPTION | No of Worker / Team | No of Worker Required | MOBILE CRANE
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
1 | SURVEY SETTING UP & LEVEL SIM PLAT INSTALLED (1 BLOCK) | 2+0 | 2 | bar: 1 to 2
2 | INSTALLATION OF PANEL WALL (1 UNIT/DAY) | 4+1 | 5 | CR 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
3 | INSTALL REBAR ( 2 DAY/UNIT) | 6+0 | 6 | CR 2
4 | INSTALL & COLUMN MOULD (2 UNIT/DAY) | 6+0 | 6 | bar: 3 to 10
5 | CASTING COLUMN (1 UNIT/DAY) | 5+0 | 5 | CR 2 | bar: 5; 7; 9
6 | INSTALL STAIRCASE LANDING MOULD,PRECAST STAIRCASE & REBAR | 4+0 | 4 | CR 2 | bar: 6; 8; 10
7 | CONCRETING LANDING SLAB STAIRCASE | 8+0 | 8 | CR 2 | bar: 9
8 | INSTALLATION 1st FLOOR BEAM MOULD, HALF SLAB & REBAR |  |  | CR 2 | bar: 7 to 10
9 | INSTALLATION CONDUCT, SANITARY & PIPING
10 | CONCRETING FLOOR SLAB | 5+0 | （5） | CR 2
11 | SETTING UP, LEVEL SIM PLAT INSTALLATION | 2+0 | （2）
12 | INSTALLATION 1st FLOOR PANEL WALL (1 UNIT/DAY) | 4+1 | （4） | CR 1 | [20 empty] | 1 | 2 | 3 | 4 | 5 | [5 empty] | 6 | 7 | 8 | 9 | 10
13 | INSTALL REBAR ( 2 DAY/UNIT) | 6+0 | （6） | CR 3
14 | INSTALL & COLUMN MOULD (1 UNIT/DAY) | 6+0 | （6）
15 | CASTING COLUMN (1 UNIT/DAY)) | 5+0 | （5） | CR 3
16 | INSTALLATION ROOF BEAM MOULD | 8+0 | （8） | CR 2
17 | REBAR ROOF BEAM
18 | CONCRETING ROOF BEAM | 5+0 | （5） | CR 2
TOTAL |  |  | 36 |  |  | 1: **; 2: 1 Month allowed 4 to 5 days for weekend
（5）as per workers from item 1 to item 8
Helping other trade
Helping other trade